## README
Instructions
This workbook contains an end-to-end DevSecOps backlog aligned to SDLC phases.
- Use the Lookups sheet for allowed values (Priority, Status, Work Item Type, Environment, Iteration).
- Import order for Azure DevOps Boards: Epics -> Features -> User Stories -> Tasks -> Test Cases.
- Parent column links children to their parent work item ID.
- Iteration Path is sample-only (Sprint 1..6); adjust to your team's cadence.
- Target Environment aligns to PoC, MVP, Dev, Test, Prod milestones.
- All content is illustrative; customize estimates, owners, and dates before importing.

## Lookups
Priority | Status | Work Item Type | Environment | Iteration
High | New | Epic | PoC | Sprint 1
Medium | In Progress | Feature | MVP | Sprint 2
Low | Blocked | User Story | Dev | Sprint 3
| Done | Task | Test | Sprint 4
|  | Test Case | Prod | Sprint 5
|  | Release |  | Sprint 6

## Epics
ID | Title | Description | Priority | Status | Area Path | Target Environment | Tags | Owner | Risk
E-001 | Planning & Governance | Initiate project, align stakeholders, define governance, and create the initial backlog. | Medium | New | Contoso.DevSecOps.Planning | Prod | Epic |  | Medium
E-002 | Requirements & Design | Capture requirements and produce system and solution designs. | Medium | New | Contoso.DevSecOps.Design | Prod | Epic |  | Medium
E-003 | Development Environment | Stand up source control, branching strategy, developer tooling, and environments. | Medium | New | Contoso.DevSecOps.DevEnv | Prod | Epic |  | Medium
E-004 | Infrastructure as Code | Provision and configure cloud infrastructure using pipelines and IaC. | High | New | Contoso.DevSecOps.IaC | Prod | Epic |  | Medium
E-005 | Application Build & Test | Automate build, unit/integration testing, and quality gates. | Medium | New | Contoso.DevSecOps.BuildTest | Prod | Epic |  | Medium
E-006 | Security & Quality (DevSecOps) | Shift-left security scanning (SAST/DAST/dependency), policies, and compliance. | High | New | Contoso.DevSecOps.Security | Prod | Epic |  | Medium
E-007 | Release & Deployment | Automate multi-stage releases with safe rollout strategies (canary/blue-green). | High | New | Contoso.DevSecOps.Release | Prod | Epic |  | Medium
E-008 | Monitoring & Feedback | Collect logs/metrics/traces, set SLO/SLAs, enable alerting and feedback loops. | Medium | New | Contoso.DevSecOps.Observability | Prod | Epic |  | Medium
E-009 | Documentation & Training | Produce living documentation and enablement for users and operations. | Medium | New | Contoso.DevSecOps.Enablement | Prod | Epic |  | Medium
E-010 | Maintenance & Enhancements | Operate, patch, and iterate on features based on telemetry and feedback. | Medium | New | Contoso.DevSecOps.Operations | Prod | Epic |  | Medium

## Features
ID | Title | Description | Parent | Priority | Status | Area Path | Target Environment | Tags | Owner | Risk
F-001 | Project Kickoff & Charter | Define goals, scope, stakeholders, and success criteria. | E-001 | Medium | New | Contoso.DevSecOps.Planning | Dev | Feature |  | Medium
F-002 | Azure DevOps Project & Boards | Create ADO project, teams, area/iteration paths, and permissions. | E-001 | Medium | New | Contoso.DevSecOps.Planning | Dev | Feature |  | Medium
F-003 | Backlog & Roadmap | Seed epics/features/stories and prioritize roadmap. | E-001 | Medium | New | Contoso.DevSecOps.Planning | Dev | Feature |  | Medium
F-004 | Requirements Capture | Elicit functional/non-functional requirements and constraints. | E-002 | Medium | New | Contoso.DevSecOps.Design | Dev | Feature |  | Medium
F-005 | Solution Architecture | Define system context, components, and interfaces. | E-002 | Medium | New | Contoso.DevSecOps.Design | Dev | Feature |  | Medium
F-006 | Threat Modeling | Identify threats and mitigations for critical flows. | E-002 | Medium | New | Contoso.DevSecOps.Design | Dev | Feature |  | Medium
F-007 | GitHub Enterprise Repos | Create repos and link to ADO work items. | E-003 | Medium | New | Contoso.DevSecOps.DevEnv | Dev | Feature |  | Medium
F-008 | Branching & Policies | Establish branching, PR checks, and code owners. | E-003 | Medium | New | Contoso.DevSecOps.DevEnv | Dev | Feature |  | Medium
F-009 | Developer Workstations | DevContainers/VS Code setup with preconfigured tooling. | E-003 | Medium | New | Contoso.DevSecOps.DevEnv | Dev | Feature |  | Medium
F-010 | Landing Zone | Baseline networking, identity, and governance. | E-004 | Medium | New | Contoso.DevSecOps.IaC | Dev | Feature |  | Medium
F-011 | App Service & AKS Option | Provision runtime via Bicep/Terraform with pipelines. | E-004 | Medium | New | Contoso.DevSecOps.IaC | Dev | Feature |  | Medium
F-012 | Key Vault & Secrets | Centralize secrets and integrate with apps and pipelines. | E-004 | Medium | New | Contoso.DevSecOps.IaC | Dev | Feature |  | Medium
F-013 | CI with GitHub Actions | Build, test, and publish artifacts on each PR/merge. | E-005 | Medium | New | Contoso.DevSecOps.BuildTest | Dev | Feature |  | Medium
F-014 | Test Automation | Unit, integration, and smoke tests with coverage thresholds. | E-005 | Medium | New | Contoso.DevSecOps.BuildTest | Dev | Feature |  | Medium
F-015 | Quality Gates | Static analysis and coverage thresholds gating merges. | E-005 | Medium | New | Contoso.DevSecOps.BuildTest | Dev | Feature |  | Medium
F-016 | Advanced Security | Enable code/secret/dependency scanning and SARIF reporting. | E-006 | High | New | Contoso.DevSecOps.Security | Dev | Feature |  | Medium
F-017 | IaC Security | Validate Bicep/Terraform with policy-as-code and scanners. | E-006 | High | New | Contoso.DevSecOps.Security | Dev | Feature |  | Medium
F-018 | Container Security | SCA and image scanning; sign and attest images. | E-006 | High | New | Contoso.DevSecOps.Security | Dev | Feature |  | Medium
F-019 | Multi-Stage Environments | Dev→Test→Prod with approvals and gates. | E-007 | High | New | Contoso.DevSecOps.Release | Prod | Feature |  | Medium
F-020 | Blue-Green/Canary | Implement progressive delivery with safe rollback. | E-007 | High | New | Contoso.DevSecOps.Release | Prod | Feature |  | Medium
F-021 | API Management & AFD | Expose APIs and global routing with health probes. | E-007 | High | New | Contoso.DevSecOps.Release | Prod | Feature |  | Medium
F-022 | Azure Monitor & Logs | Central logging/metrics with dashboards and alerts. | E-008 | Medium | New | Contoso.DevSecOps.Observability | Dev | Feature |  | Medium
F-023 | Tracing & SLOs | Distributed tracing and error budgets. | E-008 | Medium | New | Contoso.DevSecOps.Observability | Dev | Feature |  | Medium
F-024 | Incident Response | Runbooks, on-call, and problem management. | E-008 | Medium | New | Contoso.DevSecOps.Observability | Dev | Feature |  | Medium
F-025 | Runbooks & README | Operational docs and developer onboarding. | E-009 | Medium | New | Contoso.DevSecOps.Enablement | Dev | Feature |  | Medium
F-026 | Architecture Docs | Diagrams and ADRs kept in repo. | E-009 | Medium | New | Contoso.DevSecOps.Enablement | Dev | Feature |  | Medium
F-027 | End-User Training | Training plan and materials for releases. | E-009 | Medium | New | Contoso.DevSecOps.Enablement | Dev | Feature |  | Medium
F-028 | Patch & Upgrade | OS/runtime dependency patching cadence. | E-010 | Medium | New | Contoso.DevSecOps.Operations | Dev | Feature |  | Medium
F-029 | Performance Tuning | Capacity planning and autoscale tuning. | E-010 | Medium | New | Contoso.DevSecOps.Operations | Dev | Feature |  | Medium
F-030 | Backlog Refinement | Data-driven enhancements from telemetry. | E-010 | Medium | New | Contoso.DevSecOps.Operations | Dev | Feature |  | Medium

## UserStories
ID | Title | Description | Acceptance Criteria | Parent | Priority | Status | Area Path | Iteration Path | Target Environment | Story Points | Tags
US-001 | Define success metrics | As a team member, I want define success metrics so that we achieve the feature outcome. | - Success metrics documented - Stakeholder sign-off - Metrics mapped to OKRs | F-001 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 3 | UserStory
US-002 | Identify stakeholders & RACI | As a team member, I want identify stakeholders & raci so that we achieve the feature outcome. | - RACI matrix approved - Meetings cadence set | F-001 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 3 | UserStory
US-003 | Governance model | As a team member, I want governance model so that we achieve the feature outcome. | - Decision log created - Change control defined | F-001 | Medium | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 3 | UserStory
US-004 | Create ADO project | As a team member, I want create ado project so that we achieve the feature outcome. | - Project exists - Area/iteration paths created - Security groups set | F-002 | High | New | Contoso.DevSecOps.Planning | Sprint 4 | Dev | 3 | UserStory
US-005 | Enable Boards & templates | As a team member, I want enable boards & templates so that we achieve the feature outcome. | - Process selected - Work item types customized | F-002 | Medium | New | Contoso.DevSecOps.Planning | Sprint 5 | Dev | 3 | UserStory
US-006 | Define Definition of Done | As a team member, I want define definition of done so that we achieve the feature outcome. | - DoD documented in repo - QA and security gates included | F-002 | Medium | New | Contoso.DevSecOps.Planning | Sprint 6 | Dev | 3 | UserStory
US-007 | Seed initial backlog | As a team member, I want seed initial backlog so that we achieve the feature outcome. | - Epics/features/stories created - Prioritized by value | F-003 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 3 | UserStory
US-008 | Roadmap view | As a team member, I want roadmap view so that we achieve the feature outcome. | - Quarterly roadmap published - Dependencies identified | F-003 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 3 | UserStory
US-009 | Refinement ceremony setup | As a team member, I want refinement ceremony setup so that we achieve the feature outcome. | - Recurring refinement on calendar | F-003 | Low | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 3 | UserStory
US-010 | Capture functional requirements | As a team member, I want capture functional requirements so that we achieve the feature outcome. | - Use cases documented - Acceptance criteria defined | F-004 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 3 | UserStory
US-011 | NFRs documented | As a team member, I want nfrs documented so that we achieve the feature outcome. | - Performance, reliability, security NFRs captured | F-004 | High | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 3 | UserStory
US-012 | Data model draft | As a team member, I want data model draft so that we achieve the feature outcome. | - ERD created - Data retention policy captured | F-004 | Medium | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 3 | UserStory
US-013 | System context diagram | As a team member, I want system context diagram so that we achieve the feature outcome. | - C4 model level 1 complete - Reviewed with stakeholders | F-005 | Medium | New | Contoso.DevSecOps.Design | Sprint 1 | Dev | 3 | UserStory
US-014 | Component design | As a team member, I want component design so that we achieve the feature outcome. | - C4 level 2-3 - Interfaces defined | F-005 | High | New | Contoso.DevSecOps.Design | Sprint 2 | Dev | 3 | UserStory
US-015 | ADR baseline | As a team member, I want adr baseline so that we achieve the feature outcome. | - Initial ADRs merged to repo | F-005 | Medium | New | Contoso.DevSecOps.Design | Sprint 3 | Dev | 3 | UserStory
US-016 | STRIDE workshop | As a team member, I want stride workshop so that we achieve the feature outcome. | - Threats identified - Mitigations tracked as tasks | F-006 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 3 | UserStory
US-017 | Abuse cases | As a team member, I want abuse cases so that we achieve the feature outcome. | - Top abuse cases documented | F-006 | Medium | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 3 | UserStory
US-018 | Security requirements | As a team member, I want security requirements so that we achieve the feature outcome. | - High priority controls traced to stories | F-006 | High | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 3 | UserStory
US-019 | Create repo & branch protection | As a team member, I want create repo & branch protection so that we achieve the feature outcome. | - Repo created - Branch policies enforced | F-007 | High | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 3 | UserStory
US-020 | Link PRs to work items | As a team member, I want link prs to work items so that we achieve the feature outcome. | - ADO linking policy enforced | F-007 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 3 | UserStory
US-021 | Actions OIDC to Azure | As a team member, I want actions oidc to azure so that we achieve the feature outcome. | - Federated credentials configured | F-007 | High | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 3 | UserStory
US-022 | Define branching strategy | As a team member, I want define branching strategy so that we achieve the feature outcome. | - GitFlow or Trunk documented | F-008 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 4 | Dev | 3 | UserStory
US-023 | Code owners & reviews | As a team member, I want code owners & reviews so that we achieve the feature outcome. | - CODEOWNERS file merged - Min reviewers set | F-008 | High | New | Contoso.DevSecOps.DevEnv | Sprint 5 | Dev | 3 | UserStory
US-024 | PR checks | As a team member, I want pr checks so that we achieve the feature outcome. | - Build, tests, lint required | F-008 | High | New | Contoso.DevSecOps.DevEnv | Sprint 6 | Dev | 3 | UserStory
US-025 | DevContainer config | As a team member, I want devcontainer config so that we achieve the feature outcome. | - .devcontainer added - Toolchain cached | F-009 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 3 | UserStory
US-026 | Pre-commit hooks | As a team member, I want pre-commit hooks so that we achieve the feature outcome. | - Hooks enforce formatting and secrets checks | F-009 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 3 | UserStory
US-027 | Local debugging | As a team member, I want local debugging so that we achieve the feature outcome. | - Debug profile works in Dev | F-009 | Low | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 3 | UserStory
US-028 | Networking baseline | As a team member, I want networking baseline so that we achieve the feature outcome. | - VNETs/subnets created - NSGs and routing configured | F-010 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 3 | UserStory
US-029 | Policies & RBAC | As a team member, I want policies & rbac so that we achieve the feature outcome. | - Azure Policy set - RBAC least privilege | F-010 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 3 | UserStory
US-030 | Cost mgmt & tags | As a team member, I want cost mgmt & tags so that we achieve the feature outcome. | - Cost budget alerts - Resource tagging policy | F-010 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 3 | UserStory
US-031 | Choose runtime | As a team member, I want choose runtime so that we achieve the feature outcome. | - Decision record: App Service vs AKS | F-011 | High | New | Contoso.DevSecOps.IaC | Sprint 1 | Dev | 3 | UserStory
US-032 | Provision runtime | As a team member, I want provision runtime so that we achieve the feature outcome. | - Bicep/Terraform pipeline deploys runtime | F-011 | High | New | Contoso.DevSecOps.IaC | Sprint 2 | Dev | 3 | UserStory
US-033 | Ingress & DNS | As a team member, I want ingress & dns so that we achieve the feature outcome. | - AFD/APIM integrated - Custom domains mapped | F-011 | Medium | New | Contoso.DevSecOps.IaC | Sprint 3 | Dev | 3 | UserStory
US-034 | Create Key Vault | As a team member, I want create key vault so that we achieve the feature outcome. | - KV provisioned - Access policies set | F-012 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 3 | UserStory
US-035 | Use Key Vault references | As a team member, I want use key vault references so that we achieve the feature outcome. | - App reads secrets via managed identity | F-012 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 3 | UserStory
US-036 | Rotation policy | As a team member, I want rotation policy so that we achieve the feature outcome. | - Rotation rules configured | F-012 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 3 | UserStory
US-037 | Build pipeline | As a team member, I want build pipeline so that we achieve the feature outcome. | - Build passes on PR - Artifacts published | F-013 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 3 | UserStory
US-038 | Caching & speed | As a team member, I want caching & speed so that we achieve the feature outcome. | - Cache hits > 80% - Build time < 5 min | F-013 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 3 | UserStory
US-039 | SBOM generation | As a team member, I want sbom generation so that we achieve the feature outcome. | - SBOM artifact attached to build | F-013 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 3 | UserStory
US-040 | Unit tests | As a team member, I want unit tests so that we achieve the feature outcome. | - Coverage >= 80% | F-014 | High | New | Contoso.DevSecOps.BuildTest | Sprint 4 | Dev | 3 | UserStory
US-041 | Integration tests | As a team member, I want integration tests so that we achieve the feature outcome. | - Happy-path and failure cases pass | F-014 | High | New | Contoso.DevSecOps.BuildTest | Sprint 5 | Dev | 3 | UserStory
US-042 | Contract tests | As a team member, I want contract tests so that we achieve the feature outcome. | - Provider/consumer contracts verified | F-014 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 6 | Dev | 3 | UserStory
US-043 | Static analysis | As a team member, I want static analysis so that we achieve the feature outcome. | - Lint rules enforced - No Critical findings | F-015 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 3 | UserStory
US-044 | Build quality gate | As a team member, I want build quality gate so that we achieve the feature outcome. | - Fail build on threshold breaches | F-015 | High | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 3 | UserStory
US-045 | Artifact signing | As a team member, I want artifact signing so that we achieve the feature outcome. | - Artifacts signed with provenance | F-015 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 3 | UserStory
US-046 | Code scanning | As a team member, I want code scanning so that we achieve the feature outcome. | - SARIF results visible - Critical issues triaged | F-016 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 3 | UserStory
US-047 | Secret scanning | As a team member, I want secret scanning so that we achieve the feature outcome. | - Leak protection on - Blocking enabled on push | F-016 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 3 | UserStory
US-048 | Dependency alerts | As a team member, I want dependency alerts so that we achieve the feature outcome. | - Dependabot enabled - Policies enforced | F-016 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 3 | UserStory
US-049 | Bicep/Terraform scanning | As a team member, I want bicep/terraform scanning so that we achieve the feature outcome. | - Pipelines fail on critical | F-017 | High | New | Contoso.DevSecOps.Security | Sprint 1 | Dev | 3 | UserStory
US-050 | OPA/Conftest policies | As a team member, I want opa/conftest policies so that we achieve the feature outcome. | - Policy-as-code enforced | F-017 | Medium | New | Contoso.DevSecOps.Security | Sprint 2 | Dev | 3 | UserStory
US-051 | Drift detection | As a team member, I want drift detection so that we achieve the feature outcome. | - Detect & report drift | F-017 | Medium | New | Contoso.DevSecOps.Security | Sprint 3 | Dev | 3 | UserStory
US-052 | Image scanning | As a team member, I want image scanning so that we achieve the feature outcome. | - Critical CVEs blocked | F-018 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 3 | UserStory
US-053 | Image signing & attest | As a team member, I want image signing & attest so that we achieve the feature outcome. | - Sigstore/Notary attestations present | F-018 | Medium | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 3 | UserStory
US-054 | Runtime policies | As a team member, I want runtime policies so that we achieve the feature outcome. | - Admission controls block risky images | F-018 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 3 | UserStory
US-055 | Define environments | As a team member, I want define environments so that we achieve the feature outcome. | - Dev/Test/Prod created | F-019 | High | New | Contoso.DevSecOps.Release | Sprint 1 | Dev | 3 | UserStory
US-056 | Approvals & checks | As a team member, I want approvals & checks so that we achieve the feature outcome. | - Manual approvals set - Health checks required | F-019 | High | New | Contoso.DevSecOps.Release | Sprint 2 | Dev | 3 | UserStory
US-057 | Artifact promotions | As a team member, I want artifact promotions so that we achieve the feature outcome. | - Only signed artifacts promoted | F-019 | Medium | New | Contoso.DevSecOps.Release | Sprint 3 | Dev | 3 | UserStory
US-058 | Blue-Green setup | As a team member, I want blue-green setup so that we achieve the feature outcome. | - Switch traffic with AFD/APIM | F-020 | High | New | Contoso.DevSecOps.Release | Sprint 4 | Prod | 3 | UserStory
US-059 | Canary rules | As a team member, I want canary rules so that we achieve the feature outcome. | - Gradual rollout 5%→100% | F-020 | High | New | Contoso.DevSecOps.Release | Sprint 5 | Prod | 3 | UserStory
US-060 | Auto-rollback | As a team member, I want auto-rollback so that we achieve the feature outcome. | - Rollback on error budget breach | F-020 | High | New | Contoso.DevSecOps.Release | Sprint 6 | Prod | 3 | UserStory
US-061 | APIM provisioning | As a team member, I want apim provisioning so that we achieve the feature outcome. | - Products & policies configured | F-021 | Medium | New | Contoso.DevSecOps.Release | Sprint 1 | Prod | 3 | UserStory
US-062 | AFD routing | As a team member, I want afd routing so that we achieve the feature outcome. | - Health probes and routes configured | F-021 | Medium | New | Contoso.DevSecOps.Release | Sprint 2 | Prod | 3 | UserStory
US-063 | WAF rules | As a team member, I want waf rules so that we achieve the feature outcome. | - OWASP protections enabled | F-021 | High | New | Contoso.DevSecOps.Release | Sprint 3 | Prod | 3 | UserStory
US-064 | Log ingestion | As a team member, I want log ingestion so that we achieve the feature outcome. | - App & platform logs visible | F-022 | High | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 3 | UserStory
US-065 | Dashboards | As a team member, I want dashboards so that we achieve the feature outcome. | - Operational dashboards published | F-022 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 3 | UserStory
US-066 | Alerts | As a team member, I want alerts so that we achieve the feature outcome. | - Action groups & alerts tuned | F-022 | High | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 3 | UserStory
US-067 | Distributed tracing | As a team member, I want distributed tracing so that we achieve the feature outcome. | - Traces across services | F-023 | Medium | New | Contoso.DevSecOps.Observability | Sprint 1 | Dev | 3 | UserStory
US-068 | SLOs & error budgets | As a team member, I want slos & error budgets so that we achieve the feature outcome. | - SLOs documented - Budgets monitored | F-023 | High | New | Contoso.DevSecOps.Observability | Sprint 2 | Dev | 3 | UserStory
US-069 | User journeys | As a team member, I want user journeys so that we achieve the feature outcome. | - Top 3 journeys instrumented | F-023 | Medium | New | Contoso.DevSecOps.Observability | Sprint 3 | Dev | 3 | UserStory
US-070 | Runbooks | As a team member, I want runbooks so that we achieve the feature outcome. | - Runbooks in repo | F-024 | Medium | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 3 | UserStory
US-071 | On-call | As a team member, I want on-call so that we achieve the feature outcome. | - Rotation & escalation defined | F-024 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 3 | UserStory
US-072 | Postmortems | As a team member, I want postmortems so that we achieve the feature outcome. | - Blameless process documented | F-024 | Medium | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 3 | UserStory
US-073 | Operational README | As a team member, I want operational readme so that we achieve the feature outcome. | - Root README with quickstarts | F-025 | Low | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 3 | UserStory
US-074 | Service runbooks | As a team member, I want service runbooks so that we achieve the feature outcome. | - Common ops tasks documented | F-025 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 3 | UserStory
US-075 | Backup/restore procedures | As a team member, I want backup/restore procedures so that we achieve the feature outcome. | - Backup tested | F-025 | High | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 3 | UserStory
US-076 | C4 diagrams | As a team member, I want c4 diagrams so that we achieve the feature outcome. | - Stored as code | F-026 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 4 | Dev | 3 | UserStory
US-077 | ADRs | As a team member, I want adrs so that we achieve the feature outcome. | - ADRs template & examples | F-026 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 5 | Dev | 3 | UserStory
US-078 | Decision log | As a team member, I want decision log so that we achieve the feature outcome. | - Log auto-linked from PRs | F-026 | Low | New | Contoso.DevSecOps.Enablement | Sprint 6 | Dev | 3 | UserStory
US-079 | Training plan | As a team member, I want training plan so that we achieve the feature outcome. | - Roles & curriculum defined | F-027 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 3 | UserStory
US-080 | Guides & videos | As a team member, I want guides & videos so that we achieve the feature outcome. | - How-to guides published | F-027 | Low | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 3 | UserStory
US-081 | Release notes | As a team member, I want release notes so that we achieve the feature outcome. | - Notes per release | F-027 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 3 | UserStory
US-082 | Dependency updates | As a team member, I want dependency updates so that we achieve the feature outcome. | - Monthly update cadence | F-028 | Medium | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 3 | UserStory
US-083 | Platform patching | As a team member, I want platform patching so that we achieve the feature outcome. | - Patching playbook executed | F-028 | High | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 3 | UserStory
US-084 | Vulnerability mgmt | As a team member, I want vulnerability mgmt so that we achieve the feature outcome. | - SLA for fixes defined | F-028 | High | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 3 | UserStory
US-085 | Load testing | As a team member, I want load testing so that we achieve the feature outcome. | - Baseline throughput & latency | F-029 | Medium | New | Contoso.DevSecOps.Operations | Sprint 1 | Dev | 3 | UserStory
US-086 | Autoscale | As a team member, I want autoscale so that we achieve the feature outcome. | - Autoscale rules validated | F-029 | Medium | New | Contoso.DevSecOps.Operations | Sprint 2 | Dev | 3 | UserStory
US-087 | Cost optimization | As a team member, I want cost optimization so that we achieve the feature outcome. | - Cost per txn visible | F-029 | Medium | New | Contoso.DevSecOps.Operations | Sprint 3 | Dev | 3 | UserStory
US-088 | Telemetry-driven ideas | As a team member, I want telemetry-driven ideas so that we achieve the feature outcome. | - Top 5 enhancements prioritized | F-030 | Low | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 3 | UserStory
US-089 | User feedback loop | As a team member, I want user feedback loop so that we achieve the feature outcome. | - Feedback items triaged | F-030 | Low | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 3 | UserStory
US-090 | Quarterly planning | As a team member, I want quarterly planning so that we achieve the feature outcome. | - Next quarter OKRs set | F-030 | Medium | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 3 | UserStory

## Tasks
ID | Title | Description | Acceptance Criteria | Parent | Priority | Status | Area Path | Iteration Path | Target Environment | Estimate (hrs) | Tags
T-001 | Plan & design work (Define success metrics) | Task for story US-001 | - Work planned - Dependencies identified | US-001 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 8 | Task
T-002 | Implement & unit test (Define success metrics) | Task for story US-001 | - Code merged with PR checks - Unit tests pass | US-001 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 8 | Task
T-003 | Update docs & runbook (Define success metrics) | Task for story US-001 | - Docs merged - CHANGELOG updated | US-001 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 8 | Task
T-004 | Plan & design work (Identify stakeholders & RACI) | Task for story US-002 | - Work planned - Dependencies identified | US-002 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 8 | Task
T-005 | Implement & unit test (Identify stakeholders & RACI) | Task for story US-002 | - Code merged with PR checks - Unit tests pass | US-002 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 8 | Task
T-006 | Update docs & runbook (Identify stakeholders & RACI) | Task for story US-002 | - Docs merged - CHANGELOG updated | US-002 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 8 | Task
T-007 | Plan & design work (Governance model) | Task for story US-003 | - Work planned - Dependencies identified | US-003 | Medium | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 8 | Task
T-008 | Implement & unit test (Governance model) | Task for story US-003 | - Code merged with PR checks - Unit tests pass | US-003 | Medium | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 8 | Task
T-009 | Update docs & runbook (Governance model) | Task for story US-003 | - Docs merged - CHANGELOG updated | US-003 | Medium | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 8 | Task
T-010 | Plan & design work (Create ADO project) | Task for story US-004 | - Work planned - Dependencies identified | US-004 | High | New | Contoso.DevSecOps.Planning | Sprint 4 | Dev | 8 | Task
T-011 | Implement & unit test (Create ADO project) | Task for story US-004 | - Code merged with PR checks - Unit tests pass | US-004 | High | New | Contoso.DevSecOps.Planning | Sprint 4 | Dev | 8 | Task
T-012 | Update docs & runbook (Create ADO project) | Task for story US-004 | - Docs merged - CHANGELOG updated | US-004 | High | New | Contoso.DevSecOps.Planning | Sprint 4 | Dev | 8 | Task
T-013 | Plan & design work (Enable Boards & templates) | Task for story US-005 | - Work planned - Dependencies identified | US-005 | Medium | New | Contoso.DevSecOps.Planning | Sprint 5 | Dev | 8 | Task
T-014 | Implement & unit test (Enable Boards & templates) | Task for story US-005 | - Code merged with PR checks - Unit tests pass | US-005 | Medium | New | Contoso.DevSecOps.Planning | Sprint 5 | Dev | 8 | Task
T-015 | Update docs & runbook (Enable Boards & templates) | Task for story US-005 | - Docs merged - CHANGELOG updated | US-005 | Medium | New | Contoso.DevSecOps.Planning | Sprint 5 | Dev | 8 | Task
T-016 | Plan & design work (Define Definition of Done) | Task for story US-006 | - Work planned - Dependencies identified | US-006 | Medium | New | Contoso.DevSecOps.Planning | Sprint 6 | Dev | 8 | Task
T-017 | Implement & unit test (Define Definition of Done) | Task for story US-006 | - Code merged with PR checks - Unit tests pass | US-006 | Medium | New | Contoso.DevSecOps.Planning | Sprint 6 | Dev | 8 | Task
T-018 | Update docs & runbook (Define Definition of Done) | Task for story US-006 | - Docs merged - CHANGELOG updated | US-006 | Medium | New | Contoso.DevSecOps.Planning | Sprint 6 | Dev | 8 | Task
T-019 | Plan & design work (Seed initial backlog) | Task for story US-007 | - Work planned - Dependencies identified | US-007 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 8 | Task
T-020 | Implement & unit test (Seed initial backlog) | Task for story US-007 | - Code merged with PR checks - Unit tests pass | US-007 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 8 | Task
T-021 | Update docs & runbook (Seed initial backlog) | Task for story US-007 | - Docs merged - CHANGELOG updated | US-007 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | 8 | Task
T-022 | Plan & design work (Roadmap view) | Task for story US-008 | - Work planned - Dependencies identified | US-008 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 8 | Task
T-023 | Implement & unit test (Roadmap view) | Task for story US-008 | - Code merged with PR checks - Unit tests pass | US-008 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 8 | Task
T-024 | Update docs & runbook (Roadmap view) | Task for story US-008 | - Docs merged - CHANGELOG updated | US-008 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | 8 | Task
T-025 | Plan & design work (Refinement ceremony setup) | Task for story US-009 | - Work planned - Dependencies identified | US-009 | Low | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 8 | Task
T-026 | Implement & unit test (Refinement ceremony setup) | Task for story US-009 | - Code merged with PR checks - Unit tests pass | US-009 | Low | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 8 | Task
T-027 | Update docs & runbook (Refinement ceremony setup) | Task for story US-009 | - Docs merged - CHANGELOG updated | US-009 | Low | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | 8 | Task
T-028 | Plan & design work (Capture functional requirements) | Task for story US-010 | - Work planned - Dependencies identified | US-010 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 8 | Task
T-029 | Implement & unit test (Capture functional requirements) | Task for story US-010 | - Code merged with PR checks - Unit tests pass | US-010 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 8 | Task
T-030 | Update docs & runbook (Capture functional requirements) | Task for story US-010 | - Docs merged - CHANGELOG updated | US-010 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 8 | Task
T-031 | Plan & design work (NFRs documented) | Task for story US-011 | - Work planned - Dependencies identified | US-011 | High | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 8 | Task
T-032 | Implement & unit test (NFRs documented) | Task for story US-011 | - Code merged with PR checks - Unit tests pass | US-011 | High | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 8 | Task
T-033 | Update docs & runbook (NFRs documented) | Task for story US-011 | - Docs merged - CHANGELOG updated | US-011 | High | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 8 | Task
T-034 | Plan & design work (Data model draft) | Task for story US-012 | - Work planned - Dependencies identified | US-012 | Medium | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 8 | Task
T-035 | Implement & unit test (Data model draft) | Task for story US-012 | - Code merged with PR checks - Unit tests pass | US-012 | Medium | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 8 | Task
T-036 | Update docs & runbook (Data model draft) | Task for story US-012 | - Docs merged - CHANGELOG updated | US-012 | Medium | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 8 | Task
T-037 | Plan & design work (System context diagram) | Task for story US-013 | - Work planned - Dependencies identified | US-013 | Medium | New | Contoso.DevSecOps.Design | Sprint 1 | Dev | 8 | Task
T-038 | Implement & unit test (System context diagram) | Task for story US-013 | - Code merged with PR checks - Unit tests pass | US-013 | Medium | New | Contoso.DevSecOps.Design | Sprint 1 | Dev | 8 | Task
T-039 | Update docs & runbook (System context diagram) | Task for story US-013 | - Docs merged - CHANGELOG updated | US-013 | Medium | New | Contoso.DevSecOps.Design | Sprint 1 | Dev | 8 | Task
T-040 | Plan & design work (Component design) | Task for story US-014 | - Work planned - Dependencies identified | US-014 | High | New | Contoso.DevSecOps.Design | Sprint 2 | Dev | 8 | Task
T-041 | Implement & unit test (Component design) | Task for story US-014 | - Code merged with PR checks - Unit tests pass | US-014 | High | New | Contoso.DevSecOps.Design | Sprint 2 | Dev | 8 | Task
T-042 | Update docs & runbook (Component design) | Task for story US-014 | - Docs merged - CHANGELOG updated | US-014 | High | New | Contoso.DevSecOps.Design | Sprint 2 | Dev | 8 | Task
T-043 | Plan & design work (ADR baseline) | Task for story US-015 | - Work planned - Dependencies identified | US-015 | Medium | New | Contoso.DevSecOps.Design | Sprint 3 | Dev | 8 | Task
T-044 | Implement & unit test (ADR baseline) | Task for story US-015 | - Code merged with PR checks - Unit tests pass | US-015 | Medium | New | Contoso.DevSecOps.Design | Sprint 3 | Dev | 8 | Task
T-045 | Update docs & runbook (ADR baseline) | Task for story US-015 | - Docs merged - CHANGELOG updated | US-015 | Medium | New | Contoso.DevSecOps.Design | Sprint 3 | Dev | 8 | Task
T-046 | Plan & design work (STRIDE workshop) | Task for story US-016 | - Work planned - Dependencies identified | US-016 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 8 | Task
T-047 | Implement & unit test (STRIDE workshop) | Task for story US-016 | - Code merged with PR checks - Unit tests pass | US-016 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 8 | Task
T-048 | Update docs & runbook (STRIDE workshop) | Task for story US-016 | - Docs merged - CHANGELOG updated | US-016 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | 8 | Task
T-049 | Plan & design work (Abuse cases) | Task for story US-017 | - Work planned - Dependencies identified | US-017 | Medium | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 8 | Task
T-050 | Implement & unit test (Abuse cases) | Task for story US-017 | - Code merged with PR checks - Unit tests pass | US-017 | Medium | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 8 | Task
T-051 | Update docs & runbook (Abuse cases) | Task for story US-017 | - Docs merged - CHANGELOG updated | US-017 | Medium | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | 8 | Task
T-052 | Plan & design work (Security requirements) | Task for story US-018 | - Work planned - Dependencies identified | US-018 | High | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 8 | Task
T-053 | Implement & unit test (Security requirements) | Task for story US-018 | - Code merged with PR checks - Unit tests pass | US-018 | High | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 8 | Task
T-054 | Update docs & runbook (Security requirements) | Task for story US-018 | - Docs merged - CHANGELOG updated | US-018 | High | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 8 | Task
T-055 | Plan & design work (Create repo & branch protection) | Task for story US-019 | - Work planned - Dependencies identified | US-019 | High | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 8 | Task
T-056 | Implement & unit test (Create repo & branch protection) | Task for story US-019 | - Code merged with PR checks - Unit tests pass | US-019 | High | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 8 | Task
T-057 | Update docs & runbook (Create repo & branch protection) | Task for story US-019 | - Docs merged - CHANGELOG updated | US-019 | High | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 8 | Task
T-058 | Plan & design work (Link PRs to work items) | Task for story US-020 | - Work planned - Dependencies identified | US-020 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 8 | Task
T-059 | Implement & unit test (Link PRs to work items) | Task for story US-020 | - Code merged with PR checks - Unit tests pass | US-020 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 8 | Task
T-060 | Update docs & runbook (Link PRs to work items) | Task for story US-020 | - Docs merged - CHANGELOG updated | US-020 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 8 | Task
T-061 | Plan & design work (Actions OIDC to Azure) | Task for story US-021 | - Work planned - Dependencies identified | US-021 | High | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 8 | Task
T-062 | Implement & unit test (Actions OIDC to Azure) | Task for story US-021 | - Code merged with PR checks - Unit tests pass | US-021 | High | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 8 | Task
T-063 | Update docs & runbook (Actions OIDC to Azure) | Task for story US-021 | - Docs merged - CHANGELOG updated | US-021 | High | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 8 | Task
T-064 | Plan & design work (Define branching strategy) | Task for story US-022 | - Work planned - Dependencies identified | US-022 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 4 | Dev | 8 | Task
T-065 | Implement & unit test (Define branching strategy) | Task for story US-022 | - Code merged with PR checks - Unit tests pass | US-022 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 4 | Dev | 8 | Task
T-066 | Update docs & runbook (Define branching strategy) | Task for story US-022 | - Docs merged - CHANGELOG updated | US-022 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 4 | Dev | 8 | Task
T-067 | Plan & design work (Code owners & reviews) | Task for story US-023 | - Work planned - Dependencies identified | US-023 | High | New | Contoso.DevSecOps.DevEnv | Sprint 5 | Dev | 8 | Task
T-068 | Implement & unit test (Code owners & reviews) | Task for story US-023 | - Code merged with PR checks - Unit tests pass | US-023 | High | New | Contoso.DevSecOps.DevEnv | Sprint 5 | Dev | 8 | Task
T-069 | Update docs & runbook (Code owners & reviews) | Task for story US-023 | - Docs merged - CHANGELOG updated | US-023 | High | New | Contoso.DevSecOps.DevEnv | Sprint 5 | Dev | 8 | Task
T-070 | Plan & design work (PR checks) | Task for story US-024 | - Work planned - Dependencies identified | US-024 | High | New | Contoso.DevSecOps.DevEnv | Sprint 6 | Dev | 8 | Task
T-071 | Implement & unit test (PR checks) | Task for story US-024 | - Code merged with PR checks - Unit tests pass | US-024 | High | New | Contoso.DevSecOps.DevEnv | Sprint 6 | Dev | 8 | Task
T-072 | Update docs & runbook (PR checks) | Task for story US-024 | - Docs merged - CHANGELOG updated | US-024 | High | New | Contoso.DevSecOps.DevEnv | Sprint 6 | Dev | 8 | Task
T-073 | Plan & design work (DevContainer config) | Task for story US-025 | - Work planned - Dependencies identified | US-025 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 8 | Task
T-074 | Implement & unit test (DevContainer config) | Task for story US-025 | - Code merged with PR checks - Unit tests pass | US-025 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 8 | Task
T-075 | Update docs & runbook (DevContainer config) | Task for story US-025 | - Docs merged - CHANGELOG updated | US-025 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | 8 | Task
T-076 | Plan & design work (Pre-commit hooks) | Task for story US-026 | - Work planned - Dependencies identified | US-026 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 8 | Task
T-077 | Implement & unit test (Pre-commit hooks) | Task for story US-026 | - Code merged with PR checks - Unit tests pass | US-026 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 8 | Task
T-078 | Update docs & runbook (Pre-commit hooks) | Task for story US-026 | - Docs merged - CHANGELOG updated | US-026 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | 8 | Task
T-079 | Plan & design work (Local debugging) | Task for story US-027 | - Work planned - Dependencies identified | US-027 | Low | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 8 | Task
T-080 | Implement & unit test (Local debugging) | Task for story US-027 | - Code merged with PR checks - Unit tests pass | US-027 | Low | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 8 | Task
T-081 | Update docs & runbook (Local debugging) | Task for story US-027 | - Docs merged - CHANGELOG updated | US-027 | Low | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | 8 | Task
T-082 | Plan & design work (Networking baseline) | Task for story US-028 | - Work planned - Dependencies identified | US-028 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 8 | Task
T-083 | Implement & unit test (Networking baseline) | Task for story US-028 | - Code merged with PR checks - Unit tests pass | US-028 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 8 | Task
T-084 | Update docs & runbook (Networking baseline) | Task for story US-028 | - Docs merged - CHANGELOG updated | US-028 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 8 | Task
T-085 | Plan & design work (Policies & RBAC) | Task for story US-029 | - Work planned - Dependencies identified | US-029 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 8 | Task
T-086 | Implement & unit test (Policies & RBAC) | Task for story US-029 | - Code merged with PR checks - Unit tests pass | US-029 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 8 | Task
T-087 | Update docs & runbook (Policies & RBAC) | Task for story US-029 | - Docs merged - CHANGELOG updated | US-029 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 8 | Task
T-088 | Plan & design work (Cost mgmt & tags) | Task for story US-030 | - Work planned - Dependencies identified | US-030 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 8 | Task
T-089 | Implement & unit test (Cost mgmt & tags) | Task for story US-030 | - Code merged with PR checks - Unit tests pass | US-030 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 8 | Task
T-090 | Update docs & runbook (Cost mgmt & tags) | Task for story US-030 | - Docs merged - CHANGELOG updated | US-030 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 8 | Task
T-091 | Plan & design work (Choose runtime) | Task for story US-031 | - Work planned - Dependencies identified | US-031 | High | New | Contoso.DevSecOps.IaC | Sprint 1 | Dev | 8 | Task
T-092 | Implement & unit test (Choose runtime) | Task for story US-031 | - Code merged with PR checks - Unit tests pass | US-031 | High | New | Contoso.DevSecOps.IaC | Sprint 1 | Dev | 8 | Task
T-093 | Update docs & runbook (Choose runtime) | Task for story US-031 | - Docs merged - CHANGELOG updated | US-031 | High | New | Contoso.DevSecOps.IaC | Sprint 1 | Dev | 8 | Task
T-094 | Plan & design work (Provision runtime) | Task for story US-032 | - Work planned - Dependencies identified | US-032 | High | New | Contoso.DevSecOps.IaC | Sprint 2 | Dev | 8 | Task
T-095 | Implement & unit test (Provision runtime) | Task for story US-032 | - Code merged with PR checks - Unit tests pass | US-032 | High | New | Contoso.DevSecOps.IaC | Sprint 2 | Dev | 8 | Task
T-096 | Update docs & runbook (Provision runtime) | Task for story US-032 | - Docs merged - CHANGELOG updated | US-032 | High | New | Contoso.DevSecOps.IaC | Sprint 2 | Dev | 8 | Task
T-097 | Plan & design work (Ingress & DNS) | Task for story US-033 | - Work planned - Dependencies identified | US-033 | Medium | New | Contoso.DevSecOps.IaC | Sprint 3 | Dev | 8 | Task
T-098 | Implement & unit test (Ingress & DNS) | Task for story US-033 | - Code merged with PR checks - Unit tests pass | US-033 | Medium | New | Contoso.DevSecOps.IaC | Sprint 3 | Dev | 8 | Task
T-099 | Update docs & runbook (Ingress & DNS) | Task for story US-033 | - Docs merged - CHANGELOG updated | US-033 | Medium | New | Contoso.DevSecOps.IaC | Sprint 3 | Dev | 8 | Task
T-100 | Plan & design work (Create Key Vault) | Task for story US-034 | - Work planned - Dependencies identified | US-034 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 8 | Task
T-101 | Implement & unit test (Create Key Vault) | Task for story US-034 | - Code merged with PR checks - Unit tests pass | US-034 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 8 | Task
T-102 | Update docs & runbook (Create Key Vault) | Task for story US-034 | - Docs merged - CHANGELOG updated | US-034 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | 8 | Task
T-103 | Plan & design work (Use Key Vault references) | Task for story US-035 | - Work planned - Dependencies identified | US-035 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 8 | Task
T-104 | Implement & unit test (Use Key Vault references) | Task for story US-035 | - Code merged with PR checks - Unit tests pass | US-035 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 8 | Task
T-105 | Update docs & runbook (Use Key Vault references) | Task for story US-035 | - Docs merged - CHANGELOG updated | US-035 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | 8 | Task
T-106 | Plan & design work (Rotation policy) | Task for story US-036 | - Work planned - Dependencies identified | US-036 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 8 | Task
T-107 | Implement & unit test (Rotation policy) | Task for story US-036 | - Code merged with PR checks - Unit tests pass | US-036 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 8 | Task
T-108 | Update docs & runbook (Rotation policy) | Task for story US-036 | - Docs merged - CHANGELOG updated | US-036 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 8 | Task
T-109 | Plan & design work (Build pipeline) | Task for story US-037 | - Work planned - Dependencies identified | US-037 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 8 | Task
T-110 | Implement & unit test (Build pipeline) | Task for story US-037 | - Code merged with PR checks - Unit tests pass | US-037 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 8 | Task
T-111 | Update docs & runbook (Build pipeline) | Task for story US-037 | - Docs merged - CHANGELOG updated | US-037 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 8 | Task
T-112 | Plan & design work (Caching & speed) | Task for story US-038 | - Work planned - Dependencies identified | US-038 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 8 | Task
T-113 | Implement & unit test (Caching & speed) | Task for story US-038 | - Code merged with PR checks - Unit tests pass | US-038 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 8 | Task
T-114 | Update docs & runbook (Caching & speed) | Task for story US-038 | - Docs merged - CHANGELOG updated | US-038 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 8 | Task
T-115 | Plan & design work (SBOM generation) | Task for story US-039 | - Work planned - Dependencies identified | US-039 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 8 | Task
T-116 | Implement & unit test (SBOM generation) | Task for story US-039 | - Code merged with PR checks - Unit tests pass | US-039 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 8 | Task
T-117 | Update docs & runbook (SBOM generation) | Task for story US-039 | - Docs merged - CHANGELOG updated | US-039 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 8 | Task
T-118 | Plan & design work (Unit tests) | Task for story US-040 | - Work planned - Dependencies identified | US-040 | High | New | Contoso.DevSecOps.BuildTest | Sprint 4 | Dev | 8 | Task
T-119 | Implement & unit test (Unit tests) | Task for story US-040 | - Code merged with PR checks - Unit tests pass | US-040 | High | New | Contoso.DevSecOps.BuildTest | Sprint 4 | Dev | 8 | Task
T-120 | Update docs & runbook (Unit tests) | Task for story US-040 | - Docs merged - CHANGELOG updated | US-040 | High | New | Contoso.DevSecOps.BuildTest | Sprint 4 | Dev | 8 | Task
T-121 | Plan & design work (Integration tests) | Task for story US-041 | - Work planned - Dependencies identified | US-041 | High | New | Contoso.DevSecOps.BuildTest | Sprint 5 | Dev | 8 | Task
T-122 | Implement & unit test (Integration tests) | Task for story US-041 | - Code merged with PR checks - Unit tests pass | US-041 | High | New | Contoso.DevSecOps.BuildTest | Sprint 5 | Dev | 8 | Task
T-123 | Update docs & runbook (Integration tests) | Task for story US-041 | - Docs merged - CHANGELOG updated | US-041 | High | New | Contoso.DevSecOps.BuildTest | Sprint 5 | Dev | 8 | Task
T-124 | Plan & design work (Contract tests) | Task for story US-042 | - Work planned - Dependencies identified | US-042 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 6 | Dev | 8 | Task
T-125 | Implement & unit test (Contract tests) | Task for story US-042 | - Code merged with PR checks - Unit tests pass | US-042 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 6 | Dev | 8 | Task
T-126 | Update docs & runbook (Contract tests) | Task for story US-042 | - Docs merged - CHANGELOG updated | US-042 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 6 | Dev | 8 | Task
T-127 | Plan & design work (Static analysis) | Task for story US-043 | - Work planned - Dependencies identified | US-043 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 8 | Task
T-128 | Implement & unit test (Static analysis) | Task for story US-043 | - Code merged with PR checks - Unit tests pass | US-043 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 8 | Task
T-129 | Update docs & runbook (Static analysis) | Task for story US-043 | - Docs merged - CHANGELOG updated | US-043 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | 8 | Task
T-130 | Plan & design work (Build quality gate) | Task for story US-044 | - Work planned - Dependencies identified | US-044 | High | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 8 | Task
T-131 | Implement & unit test (Build quality gate) | Task for story US-044 | - Code merged with PR checks - Unit tests pass | US-044 | High | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 8 | Task
T-132 | Update docs & runbook (Build quality gate) | Task for story US-044 | - Docs merged - CHANGELOG updated | US-044 | High | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | 8 | Task
T-133 | Plan & design work (Artifact signing) | Task for story US-045 | - Work planned - Dependencies identified | US-045 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 8 | Task
T-134 | Implement & unit test (Artifact signing) | Task for story US-045 | - Code merged with PR checks - Unit tests pass | US-045 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 8 | Task
T-135 | Update docs & runbook (Artifact signing) | Task for story US-045 | - Docs merged - CHANGELOG updated | US-045 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 8 | Task
T-136 | Plan & design work (Code scanning) | Task for story US-046 | - Work planned - Dependencies identified | US-046 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 8 | Task
T-137 | Implement & unit test (Code scanning) | Task for story US-046 | - Code merged with PR checks - Unit tests pass | US-046 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 8 | Task
T-138 | Update docs & runbook (Code scanning) | Task for story US-046 | - Docs merged - CHANGELOG updated | US-046 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 8 | Task
T-139 | Plan & design work (Secret scanning) | Task for story US-047 | - Work planned - Dependencies identified | US-047 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 8 | Task
T-140 | Implement & unit test (Secret scanning) | Task for story US-047 | - Code merged with PR checks - Unit tests pass | US-047 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 8 | Task
T-141 | Update docs & runbook (Secret scanning) | Task for story US-047 | - Docs merged - CHANGELOG updated | US-047 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 8 | Task
T-142 | Plan & design work (Dependency alerts) | Task for story US-048 | - Work planned - Dependencies identified | US-048 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 8 | Task
T-143 | Implement & unit test (Dependency alerts) | Task for story US-048 | - Code merged with PR checks - Unit tests pass | US-048 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 8 | Task
T-144 | Update docs & runbook (Dependency alerts) | Task for story US-048 | - Docs merged - CHANGELOG updated | US-048 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 8 | Task
T-145 | Plan & design work (Bicep/Terraform scanning) | Task for story US-049 | - Work planned - Dependencies identified | US-049 | High | New | Contoso.DevSecOps.Security | Sprint 1 | Dev | 8 | Task
T-146 | Implement & unit test (Bicep/Terraform scanning) | Task for story US-049 | - Code merged with PR checks - Unit tests pass | US-049 | High | New | Contoso.DevSecOps.Security | Sprint 1 | Dev | 8 | Task
T-147 | Update docs & runbook (Bicep/Terraform scanning) | Task for story US-049 | - Docs merged - CHANGELOG updated | US-049 | High | New | Contoso.DevSecOps.Security | Sprint 1 | Dev | 8 | Task
T-148 | Plan & design work (OPA/Conftest policies) | Task for story US-050 | - Work planned - Dependencies identified | US-050 | Medium | New | Contoso.DevSecOps.Security | Sprint 2 | Dev | 8 | Task
T-149 | Implement & unit test (OPA/Conftest policies) | Task for story US-050 | - Code merged with PR checks - Unit tests pass | US-050 | Medium | New | Contoso.DevSecOps.Security | Sprint 2 | Dev | 8 | Task
T-150 | Update docs & runbook (OPA/Conftest policies) | Task for story US-050 | - Docs merged - CHANGELOG updated | US-050 | Medium | New | Contoso.DevSecOps.Security | Sprint 2 | Dev | 8 | Task
T-151 | Plan & design work (Drift detection) | Task for story US-051 | - Work planned - Dependencies identified | US-051 | Medium | New | Contoso.DevSecOps.Security | Sprint 3 | Dev | 8 | Task
T-152 | Implement & unit test (Drift detection) | Task for story US-051 | - Code merged with PR checks - Unit tests pass | US-051 | Medium | New | Contoso.DevSecOps.Security | Sprint 3 | Dev | 8 | Task
T-153 | Update docs & runbook (Drift detection) | Task for story US-051 | - Docs merged - CHANGELOG updated | US-051 | Medium | New | Contoso.DevSecOps.Security | Sprint 3 | Dev | 8 | Task
T-154 | Plan & design work (Image scanning) | Task for story US-052 | - Work planned - Dependencies identified | US-052 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 8 | Task
T-155 | Implement & unit test (Image scanning) | Task for story US-052 | - Code merged with PR checks - Unit tests pass | US-052 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 8 | Task
T-156 | Update docs & runbook (Image scanning) | Task for story US-052 | - Docs merged - CHANGELOG updated | US-052 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 8 | Task
T-157 | Plan & design work (Image signing & attest) | Task for story US-053 | - Work planned - Dependencies identified | US-053 | Medium | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 8 | Task
T-158 | Implement & unit test (Image signing & attest) | Task for story US-053 | - Code merged with PR checks - Unit tests pass | US-053 | Medium | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 8 | Task
T-159 | Update docs & runbook (Image signing & attest) | Task for story US-053 | - Docs merged - CHANGELOG updated | US-053 | Medium | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 8 | Task
T-160 | Plan & design work (Runtime policies) | Task for story US-054 | - Work planned - Dependencies identified | US-054 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 8 | Task
T-161 | Implement & unit test (Runtime policies) | Task for story US-054 | - Code merged with PR checks - Unit tests pass | US-054 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 8 | Task
T-162 | Update docs & runbook (Runtime policies) | Task for story US-054 | - Docs merged - CHANGELOG updated | US-054 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | 8 | Task
T-163 | Plan & design work (Define environments) | Task for story US-055 | - Work planned - Dependencies identified | US-055 | High | New | Contoso.DevSecOps.Release | Sprint 1 | Dev | 8 | Task
T-164 | Implement & unit test (Define environments) | Task for story US-055 | - Code merged with PR checks - Unit tests pass | US-055 | High | New | Contoso.DevSecOps.Release | Sprint 1 | Dev | 8 | Task
T-165 | Update docs & runbook (Define environments) | Task for story US-055 | - Docs merged - CHANGELOG updated | US-055 | High | New | Contoso.DevSecOps.Release | Sprint 1 | Dev | 8 | Task
T-166 | Plan & design work (Approvals & checks) | Task for story US-056 | - Work planned - Dependencies identified | US-056 | High | New | Contoso.DevSecOps.Release | Sprint 2 | Dev | 8 | Task
T-167 | Implement & unit test (Approvals & checks) | Task for story US-056 | - Code merged with PR checks - Unit tests pass | US-056 | High | New | Contoso.DevSecOps.Release | Sprint 2 | Dev | 8 | Task
T-168 | Update docs & runbook (Approvals & checks) | Task for story US-056 | - Docs merged - CHANGELOG updated | US-056 | High | New | Contoso.DevSecOps.Release | Sprint 2 | Dev | 8 | Task
T-169 | Plan & design work (Artifact promotions) | Task for story US-057 | - Work planned - Dependencies identified | US-057 | Medium | New | Contoso.DevSecOps.Release | Sprint 3 | Dev | 8 | Task
T-170 | Implement & unit test (Artifact promotions) | Task for story US-057 | - Code merged with PR checks - Unit tests pass | US-057 | Medium | New | Contoso.DevSecOps.Release | Sprint 3 | Dev | 8 | Task
T-171 | Update docs & runbook (Artifact promotions) | Task for story US-057 | - Docs merged - CHANGELOG updated | US-057 | Medium | New | Contoso.DevSecOps.Release | Sprint 3 | Dev | 8 | Task
T-172 | Plan & design work (Blue-Green setup) | Task for story US-058 | - Work planned - Dependencies identified | US-058 | High | New | Contoso.DevSecOps.Release | Sprint 4 | Prod | 8 | Task
T-173 | Implement & unit test (Blue-Green setup) | Task for story US-058 | - Code merged with PR checks - Unit tests pass | US-058 | High | New | Contoso.DevSecOps.Release | Sprint 4 | Prod | 8 | Task
T-174 | Update docs & runbook (Blue-Green setup) | Task for story US-058 | - Docs merged - CHANGELOG updated | US-058 | High | New | Contoso.DevSecOps.Release | Sprint 4 | Prod | 8 | Task
T-175 | Plan & design work (Canary rules) | Task for story US-059 | - Work planned - Dependencies identified | US-059 | High | New | Contoso.DevSecOps.Release | Sprint 5 | Prod | 8 | Task
T-176 | Implement & unit test (Canary rules) | Task for story US-059 | - Code merged with PR checks - Unit tests pass | US-059 | High | New | Contoso.DevSecOps.Release | Sprint 5 | Prod | 8 | Task
T-177 | Update docs & runbook (Canary rules) | Task for story US-059 | - Docs merged - CHANGELOG updated | US-059 | High | New | Contoso.DevSecOps.Release | Sprint 5 | Prod | 8 | Task
T-178 | Plan & design work (Auto-rollback) | Task for story US-060 | - Work planned - Dependencies identified | US-060 | High | New | Contoso.DevSecOps.Release | Sprint 6 | Prod | 8 | Task
T-179 | Implement & unit test (Auto-rollback) | Task for story US-060 | - Code merged with PR checks - Unit tests pass | US-060 | High | New | Contoso.DevSecOps.Release | Sprint 6 | Prod | 8 | Task
T-180 | Update docs & runbook (Auto-rollback) | Task for story US-060 | - Docs merged - CHANGELOG updated | US-060 | High | New | Contoso.DevSecOps.Release | Sprint 6 | Prod | 8 | Task
T-181 | Plan & design work (APIM provisioning) | Task for story US-061 | - Work planned - Dependencies identified | US-061 | Medium | New | Contoso.DevSecOps.Release | Sprint 1 | Prod | 8 | Task
T-182 | Implement & unit test (APIM provisioning) | Task for story US-061 | - Code merged with PR checks - Unit tests pass | US-061 | Medium | New | Contoso.DevSecOps.Release | Sprint 1 | Prod | 8 | Task
T-183 | Update docs & runbook (APIM provisioning) | Task for story US-061 | - Docs merged - CHANGELOG updated | US-061 | Medium | New | Contoso.DevSecOps.Release | Sprint 1 | Prod | 8 | Task
T-184 | Plan & design work (AFD routing) | Task for story US-062 | - Work planned - Dependencies identified | US-062 | Medium | New | Contoso.DevSecOps.Release | Sprint 2 | Prod | 8 | Task
T-185 | Implement & unit test (AFD routing) | Task for story US-062 | - Code merged with PR checks - Unit tests pass | US-062 | Medium | New | Contoso.DevSecOps.Release | Sprint 2 | Prod | 8 | Task
T-186 | Update docs & runbook (AFD routing) | Task for story US-062 | - Docs merged - CHANGELOG updated | US-062 | Medium | New | Contoso.DevSecOps.Release | Sprint 2 | Prod | 8 | Task
T-187 | Plan & design work (WAF rules) | Task for story US-063 | - Work planned - Dependencies identified | US-063 | High | New | Contoso.DevSecOps.Release | Sprint 3 | Prod | 8 | Task
T-188 | Implement & unit test (WAF rules) | Task for story US-063 | - Code merged with PR checks - Unit tests pass | US-063 | High | New | Contoso.DevSecOps.Release | Sprint 3 | Prod | 8 | Task
T-189 | Update docs & runbook (WAF rules) | Task for story US-063 | - Docs merged - CHANGELOG updated | US-063 | High | New | Contoso.DevSecOps.Release | Sprint 3 | Prod | 8 | Task
T-190 | Plan & design work (Log ingestion) | Task for story US-064 | - Work planned - Dependencies identified | US-064 | High | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 8 | Task
T-191 | Implement & unit test (Log ingestion) | Task for story US-064 | - Code merged with PR checks - Unit tests pass | US-064 | High | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 8 | Task
T-192 | Update docs & runbook (Log ingestion) | Task for story US-064 | - Docs merged - CHANGELOG updated | US-064 | High | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 8 | Task
T-193 | Plan & design work (Dashboards) | Task for story US-065 | - Work planned - Dependencies identified | US-065 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 8 | Task
T-194 | Implement & unit test (Dashboards) | Task for story US-065 | - Code merged with PR checks - Unit tests pass | US-065 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 8 | Task
T-195 | Update docs & runbook (Dashboards) | Task for story US-065 | - Docs merged - CHANGELOG updated | US-065 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 8 | Task
T-196 | Plan & design work (Alerts) | Task for story US-066 | - Work planned - Dependencies identified | US-066 | High | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 8 | Task
T-197 | Implement & unit test (Alerts) | Task for story US-066 | - Code merged with PR checks - Unit tests pass | US-066 | High | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 8 | Task
T-198 | Update docs & runbook (Alerts) | Task for story US-066 | - Docs merged - CHANGELOG updated | US-066 | High | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 8 | Task
T-199 | Plan & design work (Distributed tracing) | Task for story US-067 | - Work planned - Dependencies identified | US-067 | Medium | New | Contoso.DevSecOps.Observability | Sprint 1 | Dev | 8 | Task
T-200 | Implement & unit test (Distributed tracing) | Task for story US-067 | - Code merged with PR checks - Unit tests pass | US-067 | Medium | New | Contoso.DevSecOps.Observability | Sprint 1 | Dev | 8 | Task
T-201 | Update docs & runbook (Distributed tracing) | Task for story US-067 | - Docs merged - CHANGELOG updated | US-067 | Medium | New | Contoso.DevSecOps.Observability | Sprint 1 | Dev | 8 | Task
T-202 | Plan & design work (SLOs & error budgets) | Task for story US-068 | - Work planned - Dependencies identified | US-068 | High | New | Contoso.DevSecOps.Observability | Sprint 2 | Dev | 8 | Task
T-203 | Implement & unit test (SLOs & error budgets) | Task for story US-068 | - Code merged with PR checks - Unit tests pass | US-068 | High | New | Contoso.DevSecOps.Observability | Sprint 2 | Dev | 8 | Task
T-204 | Update docs & runbook (SLOs & error budgets) | Task for story US-068 | - Docs merged - CHANGELOG updated | US-068 | High | New | Contoso.DevSecOps.Observability | Sprint 2 | Dev | 8 | Task
T-205 | Plan & design work (User journeys) | Task for story US-069 | - Work planned - Dependencies identified | US-069 | Medium | New | Contoso.DevSecOps.Observability | Sprint 3 | Dev | 8 | Task
T-206 | Implement & unit test (User journeys) | Task for story US-069 | - Code merged with PR checks - Unit tests pass | US-069 | Medium | New | Contoso.DevSecOps.Observability | Sprint 3 | Dev | 8 | Task
T-207 | Update docs & runbook (User journeys) | Task for story US-069 | - Docs merged - CHANGELOG updated | US-069 | Medium | New | Contoso.DevSecOps.Observability | Sprint 3 | Dev | 8 | Task
T-208 | Plan & design work (Runbooks) | Task for story US-070 | - Work planned - Dependencies identified | US-070 | Medium | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 8 | Task
T-209 | Implement & unit test (Runbooks) | Task for story US-070 | - Code merged with PR checks - Unit tests pass | US-070 | Medium | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 8 | Task
T-210 | Update docs & runbook (Runbooks) | Task for story US-070 | - Docs merged - CHANGELOG updated | US-070 | Medium | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | 8 | Task
T-211 | Plan & design work (On-call) | Task for story US-071 | - Work planned - Dependencies identified | US-071 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 8 | Task
T-212 | Implement & unit test (On-call) | Task for story US-071 | - Code merged with PR checks - Unit tests pass | US-071 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 8 | Task
T-213 | Update docs & runbook (On-call) | Task for story US-071 | - Docs merged - CHANGELOG updated | US-071 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | 8 | Task
T-214 | Plan & design work (Postmortems) | Task for story US-072 | - Work planned - Dependencies identified | US-072 | Medium | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 8 | Task
T-215 | Implement & unit test (Postmortems) | Task for story US-072 | - Code merged with PR checks - Unit tests pass | US-072 | Medium | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 8 | Task
T-216 | Update docs & runbook (Postmortems) | Task for story US-072 | - Docs merged - CHANGELOG updated | US-072 | Medium | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | 8 | Task
T-217 | Plan & design work (Operational README) | Task for story US-073 | - Work planned - Dependencies identified | US-073 | Low | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 8 | Task
T-218 | Implement & unit test (Operational README) | Task for story US-073 | - Code merged with PR checks - Unit tests pass | US-073 | Low | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 8 | Task
T-219 | Update docs & runbook (Operational README) | Task for story US-073 | - Docs merged - CHANGELOG updated | US-073 | Low | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 8 | Task
T-220 | Plan & design work (Service runbooks) | Task for story US-074 | - Work planned - Dependencies identified | US-074 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 8 | Task
T-221 | Implement & unit test (Service runbooks) | Task for story US-074 | - Code merged with PR checks - Unit tests pass | US-074 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 8 | Task
T-222 | Update docs & runbook (Service runbooks) | Task for story US-074 | - Docs merged - CHANGELOG updated | US-074 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 8 | Task
T-223 | Plan & design work (Backup/restore procedures) | Task for story US-075 | - Work planned - Dependencies identified | US-075 | High | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 8 | Task
T-224 | Implement & unit test (Backup/restore procedures) | Task for story US-075 | - Code merged with PR checks - Unit tests pass | US-075 | High | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 8 | Task
T-225 | Update docs & runbook (Backup/restore procedures) | Task for story US-075 | - Docs merged - CHANGELOG updated | US-075 | High | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 8 | Task
T-226 | Plan & design work (C4 diagrams) | Task for story US-076 | - Work planned - Dependencies identified | US-076 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 4 | Dev | 8 | Task
T-227 | Implement & unit test (C4 diagrams) | Task for story US-076 | - Code merged with PR checks - Unit tests pass | US-076 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 4 | Dev | 8 | Task
T-228 | Update docs & runbook (C4 diagrams) | Task for story US-076 | - Docs merged - CHANGELOG updated | US-076 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 4 | Dev | 8 | Task
T-229 | Plan & design work (ADRs) | Task for story US-077 | - Work planned - Dependencies identified | US-077 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 5 | Dev | 8 | Task
T-230 | Implement & unit test (ADRs) | Task for story US-077 | - Code merged with PR checks - Unit tests pass | US-077 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 5 | Dev | 8 | Task
T-231 | Update docs & runbook (ADRs) | Task for story US-077 | - Docs merged - CHANGELOG updated | US-077 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 5 | Dev | 8 | Task
T-232 | Plan & design work (Decision log) | Task for story US-078 | - Work planned - Dependencies identified | US-078 | Low | New | Contoso.DevSecOps.Enablement | Sprint 6 | Dev | 8 | Task
T-233 | Implement & unit test (Decision log) | Task for story US-078 | - Code merged with PR checks - Unit tests pass | US-078 | Low | New | Contoso.DevSecOps.Enablement | Sprint 6 | Dev | 8 | Task
T-234 | Update docs & runbook (Decision log) | Task for story US-078 | - Docs merged - CHANGELOG updated | US-078 | Low | New | Contoso.DevSecOps.Enablement | Sprint 6 | Dev | 8 | Task
T-235 | Plan & design work (Training plan) | Task for story US-079 | - Work planned - Dependencies identified | US-079 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 8 | Task
T-236 | Implement & unit test (Training plan) | Task for story US-079 | - Code merged with PR checks - Unit tests pass | US-079 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 8 | Task
T-237 | Update docs & runbook (Training plan) | Task for story US-079 | - Docs merged - CHANGELOG updated | US-079 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | 8 | Task
T-238 | Plan & design work (Guides & videos) | Task for story US-080 | - Work planned - Dependencies identified | US-080 | Low | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 8 | Task
T-239 | Implement & unit test (Guides & videos) | Task for story US-080 | - Code merged with PR checks - Unit tests pass | US-080 | Low | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 8 | Task
T-240 | Update docs & runbook (Guides & videos) | Task for story US-080 | - Docs merged - CHANGELOG updated | US-080 | Low | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | 8 | Task
T-241 | Plan & design work (Release notes) | Task for story US-081 | - Work planned - Dependencies identified | US-081 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 8 | Task
T-242 | Implement & unit test (Release notes) | Task for story US-081 | - Code merged with PR checks - Unit tests pass | US-081 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 8 | Task
T-243 | Update docs & runbook (Release notes) | Task for story US-081 | - Docs merged - CHANGELOG updated | US-081 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | 8 | Task
T-244 | Plan & design work (Dependency updates) | Task for story US-082 | - Work planned - Dependencies identified | US-082 | Medium | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 8 | Task
T-245 | Implement & unit test (Dependency updates) | Task for story US-082 | - Code merged with PR checks - Unit tests pass | US-082 | Medium | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 8 | Task
T-246 | Update docs & runbook (Dependency updates) | Task for story US-082 | - Docs merged - CHANGELOG updated | US-082 | Medium | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 8 | Task
T-247 | Plan & design work (Platform patching) | Task for story US-083 | - Work planned - Dependencies identified | US-083 | High | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 8 | Task
T-248 | Implement & unit test (Platform patching) | Task for story US-083 | - Code merged with PR checks - Unit tests pass | US-083 | High | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 8 | Task
T-249 | Update docs & runbook (Platform patching) | Task for story US-083 | - Docs merged - CHANGELOG updated | US-083 | High | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 8 | Task
T-250 | Plan & design work (Vulnerability mgmt) | Task for story US-084 | - Work planned - Dependencies identified | US-084 | High | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 8 | Task
T-251 | Implement & unit test (Vulnerability mgmt) | Task for story US-084 | - Code merged with PR checks - Unit tests pass | US-084 | High | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 8 | Task
T-252 | Update docs & runbook (Vulnerability mgmt) | Task for story US-084 | - Docs merged - CHANGELOG updated | US-084 | High | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 8 | Task
T-253 | Plan & design work (Load testing) | Task for story US-085 | - Work planned - Dependencies identified | US-085 | Medium | New | Contoso.DevSecOps.Operations | Sprint 1 | Dev | 8 | Task
T-254 | Implement & unit test (Load testing) | Task for story US-085 | - Code merged with PR checks - Unit tests pass | US-085 | Medium | New | Contoso.DevSecOps.Operations | Sprint 1 | Dev | 8 | Task
T-255 | Update docs & runbook (Load testing) | Task for story US-085 | - Docs merged - CHANGELOG updated | US-085 | Medium | New | Contoso.DevSecOps.Operations | Sprint 1 | Dev | 8 | Task
T-256 | Plan & design work (Autoscale) | Task for story US-086 | - Work planned - Dependencies identified | US-086 | Medium | New | Contoso.DevSecOps.Operations | Sprint 2 | Dev | 8 | Task
T-257 | Implement & unit test (Autoscale) | Task for story US-086 | - Code merged with PR checks - Unit tests pass | US-086 | Medium | New | Contoso.DevSecOps.Operations | Sprint 2 | Dev | 8 | Task
T-258 | Update docs & runbook (Autoscale) | Task for story US-086 | - Docs merged - CHANGELOG updated | US-086 | Medium | New | Contoso.DevSecOps.Operations | Sprint 2 | Dev | 8 | Task
T-259 | Plan & design work (Cost optimization) | Task for story US-087 | - Work planned - Dependencies identified | US-087 | Medium | New | Contoso.DevSecOps.Operations | Sprint 3 | Dev | 8 | Task
T-260 | Implement & unit test (Cost optimization) | Task for story US-087 | - Code merged with PR checks - Unit tests pass | US-087 | Medium | New | Contoso.DevSecOps.Operations | Sprint 3 | Dev | 8 | Task
T-261 | Update docs & runbook (Cost optimization) | Task for story US-087 | - Docs merged - CHANGELOG updated | US-087 | Medium | New | Contoso.DevSecOps.Operations | Sprint 3 | Dev | 8 | Task
T-262 | Plan & design work (Telemetry-driven ideas) | Task for story US-088 | - Work planned - Dependencies identified | US-088 | Low | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 8 | Task
T-263 | Implement & unit test (Telemetry-driven ideas) | Task for story US-088 | - Code merged with PR checks - Unit tests pass | US-088 | Low | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 8 | Task
T-264 | Update docs & runbook (Telemetry-driven ideas) | Task for story US-088 | - Docs merged - CHANGELOG updated | US-088 | Low | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | 8 | Task
T-265 | Plan & design work (User feedback loop) | Task for story US-089 | - Work planned - Dependencies identified | US-089 | Low | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 8 | Task
T-266 | Implement & unit test (User feedback loop) | Task for story US-089 | - Code merged with PR checks - Unit tests pass | US-089 | Low | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 8 | Task
T-267 | Update docs & runbook (User feedback loop) | Task for story US-089 | - Docs merged - CHANGELOG updated | US-089 | Low | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | 8 | Task
T-268 | Plan & design work (Quarterly planning) | Task for story US-090 | - Work planned - Dependencies identified | US-090 | Medium | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 8 | Task
T-269 | Implement & unit test (Quarterly planning) | Task for story US-090 | - Code merged with PR checks - Unit tests pass | US-090 | Medium | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 8 | Task
T-270 | Update docs & runbook (Quarterly planning) | Task for story US-090 | - Docs merged - CHANGELOG updated | US-090 | Medium | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | 8 | Task
T-271 | Security validation (Security requirements) | Security task for story US-018 | - Findings reviewed - Critical resolved or waived | US-018 | High | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 6 | Security,Task
T-272 | Update threat model (Security requirements) | Security task for story US-018 | - Threats and mitigations current | US-018 | High | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | 6 | Security,Task
T-273 | Security validation (Rotation policy) | Security task for story US-036 | - Findings reviewed - Critical resolved or waived | US-036 | High | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 6 | Security,Task
T-274 | Update threat model (Rotation policy) | Security task for story US-036 | - Threats and mitigations current | US-036 | High | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | 6 | Security,Task
T-275 | Security validation (Artifact signing) | Security task for story US-045 | - Findings reviewed - Critical resolved or waived | US-045 | High | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 6 | Security,Task
T-276 | Update threat model (Artifact signing) | Security task for story US-045 | - Threats and mitigations current | US-045 | High | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | 6 | Security,Task
T-277 | Security validation (Code scanning) | Security task for story US-046 | - Findings reviewed - Critical resolved or waived | US-046 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 6 | Security,Task
T-278 | Update threat model (Code scanning) | Security task for story US-046 | - Threats and mitigations current | US-046 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 6 | Security,Task
T-279 | Security validation (Secret scanning) | Security task for story US-047 | - Findings reviewed - Critical resolved or waived | US-047 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 6 | Security,Task
T-280 | Update threat model (Secret scanning) | Security task for story US-047 | - Threats and mitigations current | US-047 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 6 | Security,Task
T-281 | Security validation (Bicep/Terraform scanning) | Security task for story US-049 | - Findings reviewed - Critical resolved or waived | US-049 | High | New | Contoso.DevSecOps.Security | Sprint 1 | Dev | 6 | Security,Task
T-282 | Update threat model (Bicep/Terraform scanning) | Security task for story US-049 | - Threats and mitigations current | US-049 | High | New | Contoso.DevSecOps.Security | Sprint 1 | Dev | 6 | Security,Task
T-283 | Security validation (Image scanning) | Security task for story US-052 | - Findings reviewed - Critical resolved or waived | US-052 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 6 | Security,Task
T-284 | Update threat model (Image scanning) | Security task for story US-052 | - Threats and mitigations current | US-052 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | 6 | Security,Task
T-285 | Security validation (Image signing & attest) | Security task for story US-053 | - Findings reviewed - Critical resolved or waived | US-053 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 6 | Security,Task
T-286 | Update threat model (Image signing & attest) | Security task for story US-053 | - Threats and mitigations current | US-053 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | 6 | Security,Task
T-287 | Security validation (WAF rules) | Security task for story US-063 | - Findings reviewed - Critical resolved or waived | US-063 | High | New | Contoso.DevSecOps.Release | Sprint 3 | Prod | 6 | Security,Task
T-288 | Update threat model (WAF rules) | Security task for story US-063 | - Threats and mitigations current | US-063 | High | New | Contoso.DevSecOps.Release | Sprint 3 | Prod | 6 | Security,Task

## TestCases
ID | Title | Description | Parent | Priority | Status | Area Path | Iteration Path | Environment | Test Steps | Tags
TC-001 | Test Define success metrics | Validate acceptance criteria for story US-001 | US-001 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-002 | Test Identify stakeholders & RACI | Validate acceptance criteria for story US-002 | US-002 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-003 | Test Governance model | Validate acceptance criteria for story US-003 | US-003 | Medium | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-004 | Test Create ADO project | Validate acceptance criteria for story US-004 | US-004 | High | New | Contoso.DevSecOps.Planning | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-005 | Test Enable Boards & templates | Validate acceptance criteria for story US-005 | US-005 | Medium | New | Contoso.DevSecOps.Planning | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-006 | Test Define Definition of Done | Validate acceptance criteria for story US-006 | US-006 | Medium | New | Contoso.DevSecOps.Planning | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-007 | Test Seed initial backlog | Validate acceptance criteria for story US-007 | US-007 | High | New | Contoso.DevSecOps.Planning | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-008 | Test Roadmap view | Validate acceptance criteria for story US-008 | US-008 | Medium | New | Contoso.DevSecOps.Planning | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-009 | Test Refinement ceremony setup | Validate acceptance criteria for story US-009 | US-009 | Low | New | Contoso.DevSecOps.Planning | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-010 | Test Capture functional requirements | Validate acceptance criteria for story US-010 | US-010 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-011 | Test NFRs documented | Validate acceptance criteria for story US-011 | US-011 | High | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-012 | Test Data model draft | Validate acceptance criteria for story US-012 | US-012 | Medium | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-013 | Test System context diagram | Validate acceptance criteria for story US-013 | US-013 | Medium | New | Contoso.DevSecOps.Design | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-014 | Test Component design | Validate acceptance criteria for story US-014 | US-014 | High | New | Contoso.DevSecOps.Design | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-015 | Test ADR baseline | Validate acceptance criteria for story US-015 | US-015 | Medium | New | Contoso.DevSecOps.Design | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-016 | Test STRIDE workshop | Validate acceptance criteria for story US-016 | US-016 | High | New | Contoso.DevSecOps.Design | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-017 | Test Abuse cases | Validate acceptance criteria for story US-017 | US-017 | Medium | New | Contoso.DevSecOps.Design | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-018 | Test Security requirements | Validate acceptance criteria for story US-018 | US-018 | High | New | Contoso.DevSecOps.Design | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-019 | Test Create repo & branch protection | Validate acceptance criteria for story US-019 | US-019 | High | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-020 | Test Link PRs to work items | Validate acceptance criteria for story US-020 | US-020 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-021 | Test Actions OIDC to Azure | Validate acceptance criteria for story US-021 | US-021 | High | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-022 | Test Define branching strategy | Validate acceptance criteria for story US-022 | US-022 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-023 | Test Code owners & reviews | Validate acceptance criteria for story US-023 | US-023 | High | New | Contoso.DevSecOps.DevEnv | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-024 | Test PR checks | Validate acceptance criteria for story US-024 | US-024 | High | New | Contoso.DevSecOps.DevEnv | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-025 | Test DevContainer config | Validate acceptance criteria for story US-025 | US-025 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-026 | Test Pre-commit hooks | Validate acceptance criteria for story US-026 | US-026 | Medium | New | Contoso.DevSecOps.DevEnv | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-027 | Test Local debugging | Validate acceptance criteria for story US-027 | US-027 | Low | New | Contoso.DevSecOps.DevEnv | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-028 | Test Networking baseline | Validate acceptance criteria for story US-028 | US-028 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-029 | Test Policies & RBAC | Validate acceptance criteria for story US-029 | US-029 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-030 | Test Cost mgmt & tags | Validate acceptance criteria for story US-030 | US-030 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-031 | Test Choose runtime | Validate acceptance criteria for story US-031 | US-031 | High | New | Contoso.DevSecOps.IaC | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-032 | Test Provision runtime | Validate acceptance criteria for story US-032 | US-032 | High | New | Contoso.DevSecOps.IaC | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-033 | Test Ingress & DNS | Validate acceptance criteria for story US-033 | US-033 | Medium | New | Contoso.DevSecOps.IaC | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-034 | Test Create Key Vault | Validate acceptance criteria for story US-034 | US-034 | High | New | Contoso.DevSecOps.IaC | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-035 | Test Use Key Vault references | Validate acceptance criteria for story US-035 | US-035 | High | New | Contoso.DevSecOps.IaC | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-036 | Test Rotation policy | Validate acceptance criteria for story US-036 | US-036 | Medium | New | Contoso.DevSecOps.IaC | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-037 | Test Build pipeline | Validate acceptance criteria for story US-037 | US-037 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-038 | Test Caching & speed | Validate acceptance criteria for story US-038 | US-038 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-039 | Test SBOM generation | Validate acceptance criteria for story US-039 | US-039 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-040 | Test Unit tests | Validate acceptance criteria for story US-040 | US-040 | High | New | Contoso.DevSecOps.BuildTest | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-041 | Test Integration tests | Validate acceptance criteria for story US-041 | US-041 | High | New | Contoso.DevSecOps.BuildTest | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-042 | Test Contract tests | Validate acceptance criteria for story US-042 | US-042 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-043 | Test Static analysis | Validate acceptance criteria for story US-043 | US-043 | High | New | Contoso.DevSecOps.BuildTest | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-044 | Test Build quality gate | Validate acceptance criteria for story US-044 | US-044 | High | New | Contoso.DevSecOps.BuildTest | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-045 | Test Artifact signing | Validate acceptance criteria for story US-045 | US-045 | Medium | New | Contoso.DevSecOps.BuildTest | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-046 | Test Code scanning | Validate acceptance criteria for story US-046 | US-046 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-047 | Test Secret scanning | Validate acceptance criteria for story US-047 | US-047 | High | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-048 | Test Dependency alerts | Validate acceptance criteria for story US-048 | US-048 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-049 | Test Bicep/Terraform scanning | Validate acceptance criteria for story US-049 | US-049 | High | New | Contoso.DevSecOps.Security | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-050 | Test OPA/Conftest policies | Validate acceptance criteria for story US-050 | US-050 | Medium | New | Contoso.DevSecOps.Security | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-051 | Test Drift detection | Validate acceptance criteria for story US-051 | US-051 | Medium | New | Contoso.DevSecOps.Security | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-052 | Test Image scanning | Validate acceptance criteria for story US-052 | US-052 | High | New | Contoso.DevSecOps.Security | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-053 | Test Image signing & attest | Validate acceptance criteria for story US-053 | US-053 | Medium | New | Contoso.DevSecOps.Security | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-054 | Test Runtime policies | Validate acceptance criteria for story US-054 | US-054 | High | New | Contoso.DevSecOps.Security | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-055 | Test Define environments | Validate acceptance criteria for story US-055 | US-055 | High | New | Contoso.DevSecOps.Release | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-056 | Test Approvals & checks | Validate acceptance criteria for story US-056 | US-056 | High | New | Contoso.DevSecOps.Release | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-057 | Test Artifact promotions | Validate acceptance criteria for story US-057 | US-057 | Medium | New | Contoso.DevSecOps.Release | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-058 | Test Blue-Green setup | Validate acceptance criteria for story US-058 | US-058 | High | New | Contoso.DevSecOps.Release | Sprint 4 | Prod | - Given preconditions - When action performed - Then expected results | TestCase
TC-059 | Test Canary rules | Validate acceptance criteria for story US-059 | US-059 | High | New | Contoso.DevSecOps.Release | Sprint 5 | Prod | - Given preconditions - When action performed - Then expected results | TestCase
TC-060 | Test Auto-rollback | Validate acceptance criteria for story US-060 | US-060 | High | New | Contoso.DevSecOps.Release | Sprint 6 | Prod | - Given preconditions - When action performed - Then expected results | TestCase
TC-061 | Test APIM provisioning | Validate acceptance criteria for story US-061 | US-061 | Medium | New | Contoso.DevSecOps.Release | Sprint 1 | Prod | - Given preconditions - When action performed - Then expected results | TestCase
TC-062 | Test AFD routing | Validate acceptance criteria for story US-062 | US-062 | Medium | New | Contoso.DevSecOps.Release | Sprint 2 | Prod | - Given preconditions - When action performed - Then expected results | TestCase
TC-063 | Test WAF rules | Validate acceptance criteria for story US-063 | US-063 | High | New | Contoso.DevSecOps.Release | Sprint 3 | Prod | - Given preconditions - When action performed - Then expected results | TestCase
TC-064 | Test Log ingestion | Validate acceptance criteria for story US-064 | US-064 | High | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-065 | Test Dashboards | Validate acceptance criteria for story US-065 | US-065 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-066 | Test Alerts | Validate acceptance criteria for story US-066 | US-066 | High | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-067 | Test Distributed tracing | Validate acceptance criteria for story US-067 | US-067 | Medium | New | Contoso.DevSecOps.Observability | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-068 | Test SLOs & error budgets | Validate acceptance criteria for story US-068 | US-068 | High | New | Contoso.DevSecOps.Observability | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-069 | Test User journeys | Validate acceptance criteria for story US-069 | US-069 | Medium | New | Contoso.DevSecOps.Observability | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-070 | Test Runbooks | Validate acceptance criteria for story US-070 | US-070 | Medium | New | Contoso.DevSecOps.Observability | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-071 | Test On-call | Validate acceptance criteria for story US-071 | US-071 | Medium | New | Contoso.DevSecOps.Observability | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-072 | Test Postmortems | Validate acceptance criteria for story US-072 | US-072 | Medium | New | Contoso.DevSecOps.Observability | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-073 | Test Operational README | Validate acceptance criteria for story US-073 | US-073 | Low | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-074 | Test Service runbooks | Validate acceptance criteria for story US-074 | US-074 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-075 | Test Backup/restore procedures | Validate acceptance criteria for story US-075 | US-075 | High | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-076 | Test C4 diagrams | Validate acceptance criteria for story US-076 | US-076 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-077 | Test ADRs | Validate acceptance criteria for story US-077 | US-077 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-078 | Test Decision log | Validate acceptance criteria for story US-078 | US-078 | Low | New | Contoso.DevSecOps.Enablement | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-079 | Test Training plan | Validate acceptance criteria for story US-079 | US-079 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-080 | Test Guides & videos | Validate acceptance criteria for story US-080 | US-080 | Low | New | Contoso.DevSecOps.Enablement | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-081 | Test Release notes | Validate acceptance criteria for story US-081 | US-081 | Medium | New | Contoso.DevSecOps.Enablement | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-082 | Test Dependency updates | Validate acceptance criteria for story US-082 | US-082 | Medium | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-083 | Test Platform patching | Validate acceptance criteria for story US-083 | US-083 | High | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-084 | Test Vulnerability mgmt | Validate acceptance criteria for story US-084 | US-084 | High | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-085 | Test Load testing | Validate acceptance criteria for story US-085 | US-085 | Medium | New | Contoso.DevSecOps.Operations | Sprint 1 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-086 | Test Autoscale | Validate acceptance criteria for story US-086 | US-086 | Medium | New | Contoso.DevSecOps.Operations | Sprint 2 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-087 | Test Cost optimization | Validate acceptance criteria for story US-087 | US-087 | Medium | New | Contoso.DevSecOps.Operations | Sprint 3 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-088 | Test Telemetry-driven ideas | Validate acceptance criteria for story US-088 | US-088 | Low | New | Contoso.DevSecOps.Operations | Sprint 4 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-089 | Test User feedback loop | Validate acceptance criteria for story US-089 | US-089 | Low | New | Contoso.DevSecOps.Operations | Sprint 5 | Dev | - Given preconditions - When action performed - Then expected results | TestCase
TC-090 | Test Quarterly planning | Validate acceptance criteria for story US-090 | US-090 | Medium | New | Contoso.DevSecOps.Operations | Sprint 6 | Dev | - Given preconditions - When action performed - Then expected results | TestCase

## Releases
ID | Title | Description | Environment | Status | Tags
R-001 | PoC Release | Milestone representing PoC readiness. | PoC | Planned | Release
R-002 | MVP Release | Milestone representing MVP readiness. | MVP | Planned | Release
R-003 | Dev Release | Milestone representing Dev readiness. | Dev | Planned | Release
R-004 | Test Release | Milestone representing Test readiness. | Test | Planned | Release
R-005 | Prod Release | Milestone representing Prod readiness. | Prod | Planned | Release